## Slide 1
UNDERGRADUATE THESIS · WEEKLY PROGRESS REPORT 1
Design of a Medical Multimodal-Specific Tokenizer and a Unified Data Protocol
Week 1: problem definition, dataset selection and the unified token protocol
REDOANUZZAMAN
Sichuan University · October 8, 2026

## Slide 2
Problem and goal
Week 1 · Oct 8, 2026
2
Problem
• Medical data is heterogeneous: images, ICU vital signs, surgical video, clinical text, 3D scans
• Each modality usually gets its own model and its own input format
• A single Transformer cannot read a mix of them without a shared format
Goal
• One discrete token vocabulary for all medical modalities
• One sequence format (wire format) with time and position information
• A fair comparison of tokenisation strategies on real medical tasks
Three representation strategies to compare
A. Continuous projection
Encoder output vectors are passed directly to the model (no discretisation)
B. Vector quantisation
Encoder vectors are mapped to the nearest entry of a learned codebook
C. Event-based tokens
Measurements and annotations become symbolic tokens: <VAR:HR> <VBIN:5> …

## Slide 3
Six-week plan
Week 1 · Oct 8, 2026
3
Week 1
Problem definition, datasets, unified token protocol
◀ this week
Week 2
Image tokenizer on MedMNIST: VQ vs continuous
Week 3
Time-series tokenizers on PhysioNet 2012: event / VQ / continuous
Week 4
Surgical-video tokenizers on Cataract-101; text and point-cloud interfaces
Week 5
Downstream comparison: one Transformer, all strategies and tasks
Week 6
Ablation studies, final results, thesis draft

## Slide 4
Datasets selected (open-access only)
Week 1 · Oct 8, 2026
4
Modality | Dataset | Size | Task | Licence
2D images | MedMNIST v2 (Blood / Pneumonia / Derma), 28×28 | 23,674 train images | 8 / 2 / 7-class classification | CC BY 4.0
ICU time-series | PhysioNet 2012 set-a, 37 variables + 4 static | 4,000 stays (2,799 / 599 / 602) | In-hospital mortality | ODC-By 1.0
Surgical video | Cataract-101, sampled at 2 fps, 64×64 | 101 surgeries (71 / 15 / 15) | 10-phase recognition | CC BY-NC 4.0
Clinical text | Templated notes from structured fields | — | Interface only | —
3D point cloud | Synthetic surfaces | — | Interface only | —
Why Cataract-101, not Cholec80
• Cholec80 archive returns HTTP 403 (needs CAMMA request)
• Cataract-101: closest open surgical video with phase labels
• Cholec80 loaders already written, ready if access granted
Data-handling rules
• Patient / video-level splits, fixed seed, no leakage
• Normalisation and value bins fitted on the training split only
• Request-only data (MIMIC, SCARED) is never downloaded by code

## Slide 5
Unified token protocol: 13,824-id vocabulary
Week 1 · Oct 8, 2026
5
text
image_vq
ts_vq
video_vq
pc_vq
0
13,823
← six 256-id structural ranges
Range | Ids | Meaning
special | 0–255 | <BOS> <EOS>, modality start/end, <REP:…>
dt | 256–511 | <DT:k> time gap (seconds → 30 days)
var / vbin | 512–1023 | time-series variable + quantile bin
event | 1024–1279 | expert-annotated events (e.g. phases)
segment | 1280–1535 | unsupervised clip states
text | 1536–9727 | 8,192 sub-word pieces
*_vq | 9728–13823 | 4 codebooks × 1,024 (image/ts/video/pc)
Design choices
• Fixed, non-overlapping ranges: never learned, so any tokenizer can be swapped
• Event vs segment kept apart: an annotated phase is never confused with a cluster id
• Exact time is kept in a side channel; <DT> tokens are a coarse view of it

## Slide 6
Sequence format + real example
Week 1 · Oct 8, 2026
6
Wire format
<BOS>
<TEXT_START> <REP:SUBWORD> w w w … <TEXT_END>
<DT:k> <IMAGE_START> <REP:VQ> <ROW> v v v … <ROW> … <IMAGE_END>
<DT:k> <TIME_SERIES_START> <REP:EVENT> <STATIC> <VAR:Age> <VBIN:9> … <TIME_SERIES_END>
<EOS>
Real output: short note + 12 ICU measurements (40 tokens)
<BOS> <TEXT_START> <REP:SUBWORD> <TEXT:40> <TEXT:305> <TEXT:326> <TEXT:11> <TEXT:388> <TEXT:334> <TEXT:306> <TEXT:13> <TEXT_END> <DT:0> <TIME_SERIES_START> <REP:EVENT> <STATIC> <VAR:Age> <VBIN:4> <VAR:Gender> <VBIN:1> <VAR:ICUType> <VBIN:4> <VAR:GCS> <VBIN:9> <VAR:HR> <VBIN:4> <VAR:NIDiasABP> <VBIN:10> <VAR:NIMAP> <VBIN:13> <VAR:NISysABP> <VBIN:14> <VAR:RespRate> <VBIN:7> <VAR:Temp> <VBIN:0> <VAR:Urine> <VBIN:15> <TIME_SERIES_END> <EOS>
• Each token also carries side channels: modality id, exact time (minutes), 3-D position, optional confidence
• Lossless containers: .npz shards for training and human-readable JSONL (one token per line); a validator checks every sequence

## Slide 7
Work completed this week
Week 1 · Oct 8, 2026
7
✓
Problem scope
Defined the 5 modalities, 3 strategies and the evaluation metrics: compression, reconstruction, codebook use, sequence length, downstream score
✓
Data pipeline
Download / cleaning / splitting for MedMNIST and PhysioNet 2012; Cataract-101 frame cache at 2 fps, 64×64
✓
Protocol spec v0.2
Vocabulary ranges, special tokens, time-delta buckets, wire format, side channels, storage formats
✓
Reference code
Python package medical_tokenizer: protocol, serializer, validator, JSONL export
✓
Tests
Unit + end-to-end tests on synthetic data, so the format is checked without downloads

## Slide 8
Next week and questions
Week 1 · Oct 8, 2026
8
Plan for Week 2: image tokenizer
• Train a patch autoencoder on MedMNIST (Blood / Pneumonia / Derma)
• B: vector-quantised version with a 1,024-entry codebook
• A: continuous version with the same encoder, as the baseline
• Measure reconstruction error, codebook utilisation, tokens per image
• Show reconstructed images side by side with the originals
Questions for supervisor
• Is Cataract-101 acceptable in place of Cholec80, or should I file the CAMMA data request?
• Is templated text OK for the text modality, or is MIMIC credentialed access expected?
• Is the six-week plan and its weekly scope acceptable?